## User stories
LIST OF USER STORIES
As a... [type of user] | I want/need ... [a feature/function] | so that/because... [reason why needed]

## Non-functional reqs
LIST OF NON-FUNCTIONAL REQUIREMENTS

## Knowledge acquisition tasks
LIST OF KNOWLEDGE ACQUISITION TASKS

## PRODUCT BACKLOG
PRODUCT BACKLOG
Item priority | Item description | Story points
1 | main character + weapon sprite + ammo sprite | 2
2 | code main character (movement, melee attack, range weapon) | 13
3 | enemies sprite | 1
4 | enemies movement + recoil | 8
5 | colision algorithm(impassible object, picking up loot, taking damage) | 13
6 | drop rate algorithm | 2
7 | overall UI ( hp bar of character, weapons sprite, ammo) | 5
8 | canvas/ play area/ terrain art | 2
9 | progressing through area(progression system) | 20
10 | include other power ups (shield/ movementspeed/ double dmg) | 5
11 | character screen (shows character stats) | 20
12 | upgrade weapons or stats | 20
13 | enemy progression | 8
14 | sound | 20
15 | other mob characters | 20
16 | boss | 13
17 | title screen | 5
18 | end game screen | 2
19 | save and load function | 5
20 | instructions | 2
21 | tutorial | 13
22 | pause function | 3
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67

## Sprint 1
Sprint Backlog(First Sprint)
Item priority | Item description | Story points | Assigned | Team Velocity | Overall Team Velocity
1 | main character + weapon sprite + ammo sprite | 2 | Ant | 2 | 46
2 | code main character (movement, melee attack, range weapon) | 13 | Chris | 15
3 | enemies sprite | 1 | Chris | 16
4 | enemies movement + recoil | 8 | Sean | 24
5 | colision algorithm(impassible object, picking up loot, taking damage) | 13 | All | 37
6 | drop rate algorithm | 2 | Ant | 39
7 | overall UI ( hp bar of character, weapons sprite, ammo) | 5 | Ant | 44
8 | canvas/ play area/ terrain art | 2 | Sean | 46
Worked example for Story Points
One worked example of how our group gave a story a story point’s estimate was our group met up and we used the poker cards that we were given in our lecture in week 3. The way we did this was we all read the story as many times as we wished and then we went back to back while we picked our numbers so we could not see what each other had picked and then when we said we had picked our numbers we all turned around and laid the numbers on the table. If we had mostly the same numbers e.g. a 5, 5 & 3 we would go with what number had the most. However if we were all way apart e.g. a 2, 8 & 13, then we would explain why we picked that number and why we went high or low. Then after this explanation we would pick again and repeat this method until our numbers were mostly the same.